## Copy Writing (hidden)
PROJECT | BD | DESIGNER | DEADLINE | BRIEF | TRAFFIC COMMENTS
Mc Donalds | Ongoing | Ongoing | Ongoing | Ongoing
ABSA insurance | Amani | Malik | 2022-06-10 | Copy; Rationale
Bathu | Davina & Sagar | Malik & Theo |  | Complete
Pizza Hut Double Hut Deal | Sagar | Malik | 2022-06-13 | Copy; Rationale | Copy Added. Rationale To Be Added and Approved
Smile Nigeria | Israel | Malik | 2022-06-15 | Copy; Rationale | Copy Complete. Rationale To Be Added To The Deck.
Mars MinM's | Mike | Malik | 2022-06-16 | Rationale | Copy Added. Rationale To Be Added and Approved
ABSA Insurance Kenya | Amani | Mlaik | 2022-06-17 | Copy; Rationale
Uber Pro | Mike & Sagar | Malik | W/C 20 June | Copy; Rationale
Uber Eats x4 Briefs | Amani | Malik | 2022-06-21 | Copy; Rationale
Alexander Forbes | Amani | Malik | 2022-06-21 | Copy; Rationale
Samsung Buy & Get Pitch | Pren | Malik | 2022-06-22 | Copy; Rationale
Hendler & Hart 130 Birthday Celebration | Amani | Malik | 2022-06-23 | Copy; Rationale
ABSA Inurance CSI | Amani | Malik | 2022-06-29 | Copy; Rationale
ABSA Insurance Rewards | Amani | Malik | 2022-06-29 | Copy; Rationale
Providus | Israel | Malik | on hold | Copy; Rationale
Zanaco Account Dormancy | Sagar, Davina & Amani | Malik | 2022-07-05 | Copy; Rationale
Zanaco Account Business | Sagar, Davina & Amani | Malik | 2022-07-05 | Copy; Rationale
Zanaco Private Banking | Sagar, Davina & Amani | Malik | 2022-07-05 | Copy; Rationale
Zanaco Digital Banking | Sagar, Davina & Amani | Malik | 2022-07-05 | Copy; Rationale

## Creative Schedule
PROJECTS | CREATIVE | BRIEF | DEADLINE | CLIENT MEETING | STATUS NOTES
Blank Page Afcon 2024 | Sanele | Social media posts |  |  | Sent for review
RMA Vehicle branding | Sanele | Addiing client changes | 2023-12-05 |  | Waiting approval
216 Media Brand Guide | Hlabi | Brand guide | 2023-12-08
ROA Website | Allison | Web development | 2023-12-07 | 2023-12-08 | Work in progress
216 Website | Tumelo | Web development | 2023-12-06
216 Speed App | Tumelo | App development | Ongoing |  | Review every Friday at 2pm
216 Speed Brand Identity | Dianda | Brand identity | Ongoing |  | Review every Friday at 2pm
ROA Website | Dianda | Source images for Allison | 2023-12-06 | 2023-12-08
ROA Lounge and Office | Princess | Interior Design | 2023-12-07 | 2023-12-08 | Work in progress
ROA Lounge and Office | Sli | Interior Design | 2023-12-07 | 2023-12-08 | Work in progress
4 Racing event | Refiloe | Creative concept and ideas | 2023-12-07 | 2023-12-08
Shepowher | Refiloe | Social media plan and profiles | 2023-12-06 | 2023-12-06
Blank Page Productions | Refiloe | Social media plan | 2023-12-06 | 2023-12-07
4 Racing event | Sinead | Event planning | 2023-12-07 | 2023-12-08
ROA Event | Sinead | Event planning | TBC | TBC
Womens CAF | Sinead | Event planning | TBC | TBC

## Old Creative Schedule (hidden)
PROJECTS | BD | CREATIVE | BRIEF | INTERNAL REVIEW | INTERNAL DEADLINE | CLIENT MEETING | STATUS NOTES
Reception Plasma Screen | Pren | Keenen | Video | N/A | Start in Feb 2023 | N/A
P&C Team shoot | Germaine | Stuart | Booked from 15:30 till 16:00 | N/A | TBC | N/A
TLC Vehicle Branding | Jade | Keenen | ONHOLD | N/A | W/C 27 Feb
Coke |  | Keenana & Stu | 1.Project plan ex Germaine - TBC 2. Storyboard ex Stuwie 3. Big Bonanze New name 4. Expose Video |  |  | 1. Awating approval on artwork
TLC EXPOSE Video X7 | Theo | Team | 1.TLC internal Video (Show Reel) 2.7 network videos 3. 1 Combined Network video 4.People TLC Video 5. TLC Brand TVC |  | Ongoing
P&C Staff Intro Videos | Germaine | Stuart | Ongoing weekly x4 | N/A | 31 March - x2 | N/A
TLC New Intro Video | Theo/Germaine | Stuart/Dom (Copywriter) |  |  | 2023-04-12
ONHOLD
Tent Cards | Ronnie/Germaine | Thandi | Onhold Tent card design | N/A | TBC
Coca Cola B2C Share Magic Moments | Theo | Gugu, Theo & Keenen | changes to be rolled out |  | TBC
| Majeed/Germaine | Stuart & Keenen | 1. Partners Club Logo 2. Team photos: 1 Sep 3. Template for meet the team 4. Collage image of all of our networks |  | 2022-09-25
TLC Internal Business Cards | Germaine | Thandi | Awaiting internal approval
TLC Email Signatures | Theo | Refiloe | Awaiting further instruction
UNISA RFA | Amani | Keenen | Awaitng internal approval
P&C Customer Journey Partner Video | Germaine | Stuart | Creative Complete - Awaiting script ex Germaine |  | -
Intro Tech Slide | Yoli | TBC | Morning Submission Update look and feel |  | On Hold |  | Awaiting feedback and direction from BD
Franks Cafe Menu & Summer Menu | IT | Stuart | confirm when summer menu will be launched |  | Temporary hold
Alexander Forbes | Amani | Keenen | 1 KV Customer Journey Awaiting further info ex BD |  | TBC
Note on H10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Germaine Werner to update date
Note on A11: Tintswalo Maluleke: